## Slide 1: Grade R Maths project External Evaluation Overall considerations

## Slide 2
Process theory
Impact theory
Development of resources
Capacitation of district officials
Training of Grade R teachers
Resource use for training & in the classroom
Enhanced knowledge & skills to support Grade R teachers (district officials)
Enhanced knowledge & skills to teach Grade R Maths (Grade R teachers)
Improved learner performance in Maths (readiness for Grade 1)
Effective teaching of Maths
Short-term
Medium-term
Outcomes
Long-term (impact)
Process theory Impact theory
Support to Grade R teachers
Notes: Simplified ToC – in order to answer the question How successful has the R-Maths project been in meeting its goals?
Green = achieved
Orange = partially achieved

## Slide 3: What further testing could/should take place around R-Maths?
Deeper analysis of the learners’ test results
Research to answer key questions: e.g. why did the urban isiXhosa group do so well in the Marko-D tests?
Rasch modelling on the Marko-D to check validity of isiXhosa version, and the comparison against the norms.
A delayed post-test with all 3 groups (teachers, subject advisors and learners)
Making the teacher and subject advisor test longer - and piloting it - so it then is available elsewhere as a more reliable instrument.
Notes: Referring to testing beyond the current evaluation scope
e.g. : seeing which items were well answered and which poorly; what were common wrong answers; etc. – thus, a kind of error analysis
3. But this would be expensive… and there will be some dilution of effect over time
5. [link to PrimTEd Maths test for primary teachers (does not focus directly on Grade R…)]

## Slide 4: What high-level lessons have been learnt (and recommendations can be made)?
Training programmes like these can impact SA and teacher knowledge
The SAs and teachers are generally eager to learn more about Grade R Maths, and are willing to attend related training programmes over many days
Academic institutions and provincial departments of education can successfully work together to implement programmes – but more frequent consultation is needed
Trust is very important in ensuring a smooth and effective collaboration. More time should be invested establishing this upfront.

## Slide 5: Lessons learnt and recommendations (2)
The modified cascade model has had some success (impact on SAs and teachers’ knowledge, but less on classroom practice and learner performance )
More support is needed for Grade R teachers in how they implement the new learnings in the classroom.
Subject advisors generally have too big a work load – so cannot observe teachers in the classroom often enough.
It would have been better to pilot the intervention first, and then scale up to go province-wide
A design-based evaluation would have allowed for changes (improvement) to the R-Maths programme prior to scale up
Notes: Support: Classroom observations and feedback are needed for this – but see next point…
SA work load: There is a role for HoDs to monitor and Grade R teachers to provide peer support/monitoring. WCED reported that they have developed a monitoring tool to be used by principals and HoDs. This is particularly important for small schools where the teacher attending training may be the only Grade R teacher in their school and not have peers to support them to implement.

## Slide 6: Lessons learnt and recommendations (3)
It would have been better to have less variation in the roll-out model and to roll-out in a way that was more conducive to the impact evaluation
A longer timeframe would have been preferable for materials development (and piloting).
The PSC should have been established at the outset, ideally by the project sponsor (senior manager) within government.
Notes: Roll out variation: each district did their own thing – appears to be leading to Phase 2 problems
Impact conducive: needed to have intervention and comparison groups more similar

## Slide 7: What needs to happen to ensure this project (and its impact) is sustainable?
Further support for teachers’ implementation in the classroom, monitoring by HoDs and peer support by other Grade R teachers.
SAs workload being changed to allow for classroom observations – or some alternative support model
No new Grade R interventions in the WC for at least one year Phase 2 of R-Maths is implemented using the lessons learnt from Phase 1
Notes: No new interventions: – to give a chance for ELIT and R-Maths to embed itself

## Slide 8: Sustainability suggestions (2)
Training of SAs and Grade R teachers who missed the initial R-Maths training
Variations in the model (block training reduced to 4 days, condense cluster workshops/training for teachers from “good” schools to be tested.
Focussing on building the capacity of the weaker SAs
Plans to be put in place for the procurement of replacement/additional R-Maths materials.
Notes: Training of newbies: R-Maths training to be offered as part and parcel of induction for new teachers and refresher training (ELIT and R-Maths) to be offered on a rotational basis.